## Sheet1
Sprint Progress report
Task ID | Task Name | Status | Assigned To | Expected Completion | Comments/Blockers
TASK-007 | Refactor Data Handling System | Completed | Meghana Kilaru, Naga Sahithya Nagisetty | 2025-03-26 | Successfully completed. Data flow between backend and frontend is stable.
TASK-008 | Connect Frontend with Backend | In Progress | Keerthi Yetukuri, Saketh Gogineni | 2025-04-08 | Strapi and npm-related issues; still resolving and testing integration.
TASK-010 | Improve Recommendation Algorithm | In Progress | Meghana Kilaru, Naga Sahithya Nagisetty | 2025-04-08 | Initial optimization complete; working on improving result quality further.
TASK-011 | Error Rectification and Testing | Pending | Saketh Gogineni, Meghana Kilaru | 2025-04-07 | Scheduled for testing after frontend-backend integration is stabilized