## Sheet1
Sprint Progress Report
Task ID | Task Name | Status | Assigned To | Expected Completion | Comments/Blockers
TASK-006 | Improve HUIM Algorithm | Completed | Naga Sahithya Nagisetty | 2025-03-04 | Trying to improve precision, recall, and F1 score values
TASK-007 | Create Data API | In Progress | Meghana Kilaru | 2025-03-26 | API under development, collaborating with Saketh Gogineni
TASK-008 | Improve Data Visualization | In Progress | Saketh Gogineni | 2025-03-26 | Enhancing graphs for better clarity
TASK-009 | Connect Frontend with Backend | In Progress | Naga Sahithya Nagisetty | 2025-03-22 | Collaborating with Keerthi Yetukuri
TASK-010 | Add User Login System | Completed | Keerthi Yetukuri | 2025-03-10 | User login system integrated and tested successfully