## Sheet1
Sprint Progress Report
Task ID | Task Name | Status | Assigned To | Expected Completion | Comments/Blockers
TASK-007 | Create Data API | Completed | Meghana Kilaru, Naga Sahithya Nagisetty | 2025-03-26 | API is under development and working fine for frontend integration
TASK-008 | Connect Frontend with Backend | In Progress | Keerthi Yetukuri, Saketh Gogineni | 2025-04-08 | Errors occurred(strapi and npm error). Trying to modify.
TASK-010 | Optimize the Recommendation Algorithm | In Progress | Meghana Kilaru, Naga Sahithya Nagisetty | 2025-04-08 | Algorithm optimization done but still looking for better recommendations